## Read me
Enterprise Risk Register & Treatment Plan: Apex Bank Ltd.
Objective: Design an audit-ready, 5x4 risk matrix tracking cyber, physical, operational, and compliance risks for a commercial bank.
Framework & Methodology: Outline the scoring model (Likelihood \times Impact = Score) aligned with ISO 27005 / NIST SP 800-30 standards.
Key Risk Domains Covered: Cybersecurity (EDR, MFA, Malware), Infrastructure (DR/BCP, ATM uptime), Compliance (CBN/NDIC reporting automation), and Physical Access.

## Risk register
ID | Risk description | Category | Threat | Vulnerability | Likelihood (1-4) | Impact (1-5) | Inherent Risk Score | Current controls | Owner | Risk Treatment | Residual likelihood | Residual impact | Residual Risk Score | Due Date | Mitigation status | Last Updated | Notes
R2026-01 | Employee phishing attack | Cybersecurity | A cybercriminal sends a deceptive email to an employee to steal their login credentials. | Employee lacks adequate phishing awareness / MFA is not enabled. | 4 | 5 | 20 | Inconsistent cybersecurity training. Irregular phishing simulations | IT Security Lead | Conduct quarterly cybersecurity training. Consistent phishing simulations. Enforce MFA to block unauthorized logins. | 2 | 2 | 4 | 2026-08-31 | In Progress | 2026-08-18 | Cybersecurity training commences on the 1st of September. Phishing simulations rollout and MFA implementations underway.
R2026-02 | Customer data breach | Information Security | An unauthorized actor, malicious insider, or external attacker attempts to exfiltrate sensitive customer data (PII, account details) from bank databases. | Weak database encryption, unpatched system vulnerabilities, lack of strict Data Loss Prevention controls and access monitoring | 3 | 5 | 15 | Encryption, IDS, Access Control Lists | CISO | Deploy DLP Solution, enforce strict database encryption, and mandata quarterly access audits. | 2 | 2 | 4 | 2026-08-30 | In Progress | 2026-08-18 | Implementation of DLP solution deployed. Database encryption audit scheduled for Q3.
R2026-03 | ATM network disruption | Operational | Fiber cut, power outage, telecom link failure, DDoS attack targeting ATM switch. | Lack of redundant network connections, insufficient backup power, outdated network infrastructure. | 4 | 4 | 16 | Primary ISP network link, baseline generator power backup at central nodes. | Head of Infrastructure or IT Ops | Procure redundant secondary telecom links (dual ISP) and install uninterruptible power supply at all critical ATM locations. | 1 | 2 | 2 | 2026-08-30 | In Progress | 2026-08-18 | Procurement of redundant ISP links underway. Secondary failover testing scheduled with network operations team.
R2026-04 | Unauthorized privileged access | Access Management | A malicious insider or external attacker attempts to gain administrative or elevated access permissions to critical banking systems. | Lack of Privileged Access Management, weak password policies, shared admin accounts, and absence of MFA for admin logins | 4 | 5 | 20 | Basic role-based access controls (RBAC) and manual admin access approvals | IAM Lead | Deploy a dedicated Privileged Access Management solution, mandate MFA for all admin logins, and implement automated session logging. | 1 | 2 | 2 | 2026-08-30 | In Progress | 2026-08-18 | PAM procurement finalized. MFA enforcement for administrative accounts deployed.
R2026-05 | Former employee access not revoked | Access Management | A terminated employee utilizes active credentials to gain unauthorized access to sensitive files and internal banking systems. | Delayed HR offboarding workflows, lack of automated Identity Management synchronization across systems. | 4 | 5 | 20 | Manual HR exit notification checklist and periodic access reviews | HR / IAM Lead | Integrate HR portal with Active Directory/SSO for automated same-day account deprovisioning upon employee termination. | 1 | 2 | 2 | 2026-08-30 | In Progress | 2026-08-18 | API integration between the HR management system and Active Directory was initiated to automate real-time deprovisioning during offboarding.
R2026-06 | Core banking system outage | Operational | Hardware failure, unhandled software bugs, ransomware attacks | Outdated Disaster Recovery configurations, minimal failover mechanisms. | 4 | 4 | 16 | Daily database backups, standard failover configuration, secondary Disaster Recovery site. | Head of IT Ops | Conduct quarterly automated DR failover tests, enforce a 1-hour Recovery Time Objective, deploy active-active database clustering | 1 | 3 | 3 | 2026-09-15 | In Progress | 2026-08-23 | Core database clustering migration underway. Next scheduled DR failover simulation set for Q3.
R2026-07 | Third-party SaaS failure | Third-Party Risk | A key SaaS vendor (e.g., cloud CRM, payment gateway, or KYC provider) experiences an extended service outage, security breach, or operational insolvency | Over-reliance on a single vendor without contingency/fallback systems, lack of rigid SLAs, and insufficient vendor risk monitoring. | 4 | 4 | 16 | Basic SLAs and annual vendor SOC 2 review | Head of Vendor Risk Management / Procurement Lead | Establish secondary backup providers for critical services, mandate continuous vendor monitoring, and enforce strict contractual downtime penalties. | 2 | 3 | 6 | 2026-09-15 | In Progress | 2026-08-23 | Third-party SaaS risk assessment ongoing. Secondary Payment gateway fallback integration currently in testing.
R2026-08 | Malware infection | Cybersecurity | Cybercriminals execute ransomware, spyware, or malicious scripts via infected email attachments, compromised downloads, and removable drives. | Outdated antivirus, unpatched operating systems, lack of Endpoint Detection and Response (EDR), and unmanaged USB drive access. | 4 | 5 | 20 | Antivirus software, manual OS patching updates, network IDS/IDPS | CISO/Head of IT Security | Deploy Endpoint Detection and Response, set up automated OS patch management, and enforce USB device blocking via Group Policy. | 1 | 2 | 2 | 2026-09-15 | In Progress | 2026-08-23 | EDR software rollout initiated across all workstation endpoints, automated patch management server deployment in progress.
R2026-09 | Regulatory reporting error | Compliance | Regulatory bodies (e,g., CBN, NDIC) imposing sanctions, heavy fines, or operational license suspension due to inaccurate, late, or non-compliant financial and data privacy reporting. | Manual data extraction processes, reliance on legacy spreadsheets, lack of automated validation checks, and unclear ownership of regulatory submission deadlines. | 3 | 4 | 12 | Manual review process, statutory reporting checklists, and legacy spreadsheet reconciliations. | Compliance Officer | Implement automated RegTech reporting software, enforce pre-submission validation scripts, and establish an automated compliance tracking calendar. | 1 | 2 | 2 | 2026-09-15 | Closed | 2026-08-23 | RegTech automation vendor procurement finalized, automated pre-submission data validation workflows currently under configuration.
R2026-10 | Physical access to server room | Physical Security | Unauthorized individuals, rogue employees, or maintenance contractors gain physical entry to core server rooms, resulting in hardware tampering, data theft, or physical disruption. | Legacy keycard locks, missing biometric multi-factor authentication, blind spots in CCTV coverage, and unmonitored visitor access logs. | 4 | 4 | 16 | Keycard access readers, paper-based visitor logbook, and basic CCTV camera monitoring. | Head of Physical Security or Chief Infrastructure Officer | Upgrade to dual-factor biometric access control, mandate two-person integrity escort policies for third-party vendors, and expand 24/7 CCTV surveillance coverage with motion-triggered alerting. | 2 | 3 | 6 | 2026-09-15 | In Progress | 2026-08-23 | Biometric access control procurement in progress, vendor site survey scheduled for full CCTV coverage expansion.

## Scoring key
4 x 5 Risk Heat Map (Likelihood x Impact)
Impact ->
|  | 1 | 2 | 3 | 4 | 5
Likelihood | 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
Bands: Green 1-6 (low) Amber 7-12 (medium) Red 13-20 (priority)
Likelihood scale: 1 Rare 2 Unlikely 3 Possible 4 Likely
Impact scale: 1 Negligible 2 Minor 3 Moderate 4 Major 5 Severe

## Treatment plans
Risk ID | Mitigation action | Owner | Target date | Status | Verification / proof | Notes
R2026-01 | Conduct quarterly cybersecurity training. Consistent phishing simulations. Enforce MFA to block unauthorized logins. | IT Security Lead | 2026-08-31 | In Progress | Phishing campaign report & Azure AD MFA enforcement logs | Q3 training module scheduled for Sept 1
R2026-02 | Deploy DLP Solution, enforce strict database encryption, and mandata quarterly access audits. | CISO | 2026-08-30 | Closed | DLP agent deployment report & Database encryption audit sign-off | DLP rule tuning completed
R2026-03 | Procure redundant secondary telecom links (dual ISP) and install uninterruptible power supply at all critical ATM locations. | Head of Infrastructure or IT Ops | 2026-08-30 | In Progress | Executed ISP SLA contract & Network failover test results | Secondary ISP link installation in progress
R2026-04 | Deploy a dedicated Privileged Access Management solution, mandate MFA for all admin logins, and implement automated session logging. | IAM Lead | 2026-08-30 | In Progress | CyberArk / PAM vendor PO & Admin session audit trail | PAM procurement finalized
R2026-05 | Integrate HR portal with Active Directory/SSO for automated same-day account deprovisioning upon employee termination. | HR / IAM Lead | 2026-08-30 | In Progress | API integration specs & HR-to-AD sync test logs | API connection setup initiated
R2026-06 | Conduct quarterly automated DR failover tests, enforce a 1-hour Recovery Time Objective, deploy active-active database clustering | Head of IT Ops | 2026-09-15 | In Progress | DR Test Sign-off Sheet & RTO benchmark log | Failover test scheduled for Q3
R2026-07 | Establish secondary backup providers for critical services, mandate continuous vendor monitoring, and enforce strict contractual downtime penalties. | Head of Vendor Risk Management / Procurement Lead | 2026-09-15 | In Progress | Vendor SOC 2 Type II report & Fallback routing test results | Secondary gateway API integration in sandbox
R2026-08 | Deploy Endpoint Detection and Response, set up automated OS patch management, and enforce USB device blocking via Group Policy. | CISO/Head of IT Security | 2026-09-15 | In Progress | CrowdStrike / EDR console dashboard & Active Directory GPO export | EDR agent roll-out at 75%
R2026-09 | Implement automated RegTech reporting software, enforce pre-submission validation scripts, and establish an automated compliance tracking calendar. | Compliance Officer | 2026-09-15 | In Progress | RegTech software license agreement & Test run validation outputs | Data mapping phase active
R2026-10 | Upgrade to dual-factor biometric access control, mandate two-person integrity escort policies for third-party vendors, and expand 24/7 CCTV surveillance coverage with motion-triggered alerting. | Head of Physical Security or Chief Infrastructure Officer | 2026-09-15 | In Progress | Vendor site survey report & Biometric hardware procurement invoice | Site survey completed by vendor